## Tasks
id | parent | text | type | start | end | duration | optimistic | pessimistic | progress | resources | url | details | open | unscheduled | base_start | base_end
1 |  | Project Root | summary | 2023-12-06 | 2023-12-14 | 8 |  |  | 60 |  |  | Main project container with all tasks | TRUE
2 | 1 | Task 1 | task | 2023-12-06 | 2023-12-10 | 4 |  |  | 80 | R001, R002 |  | First phase of the project work |  |  | 2023-12-05 | 2023-12-09
3 | 1 | Task 2 | task | 2023-12-11 | 2023-12-15 | 4 | 10 | 15 | 40 | R003 | https://example.com/task2 | Second phase following Task 1 |  |  | 2023-12-11 | 2023-12-15
4 |  | A | task | 2023-12-09 | 2023-12-16 | 7 |  |  | 0 | R001 |  |  |  | FALSE
5 |  | B | task | 2023-12-12 | 2023-12-13 | 1 |  |  | 0 | R002 |  |  |  | FALSE | 2023-12-12 | 2023-12-13
6 |  | C | task | 2023-12-14 | 2023-12-15 | 1 |  |  | 0 | R003 |  |  |  | FALSE | 2023-12-14 | 2023-12-15
7 |  | D | task | 2023-12-19 | 2023-12-20 | 1 |  |  | 0 | R001 |  |  |  | FALSE | 2023-12-19 | 2023-12-20

## Links
id | source | target | type
1 | 2 | 3 | e2s
2 | 5 | 6 | e2s
3 | 6 | 7 | e2s